## Data Base
Tag | Item Class | Description | Functional Location | Last Insp/ | Freq/ (SAP) | Next Insp/ | Year | Due Date | Compl/ date | PMonth Insp | CMonth Insp | SECE STATUS | Delay | M. Item | M. Plan | Job Done | Days in Backlog | Backlog?
TA1000 | Corrosion Monitoring | Corrosion Monitoring inspection for TA1000 | GIR/FPSOH/INERT/TA1000 | 29/07/2024 | 12 | 29/07/2025 | 2025 | 2025-07-29 | 0 | 7 | 11 |  | < 6 Months | 30025000 | AOGIRTA1000 | Not Compl | 95 | Yes
TA1001 | Corrosion Monitoring | Corrosion Monitoring inspection for TA1001 | GIR/DECK/ELEC/TA1001 | 04/07/2024 | 12 | 04/07/2025 | 2025 | 2025-07-04 | 0 | 7 | 11 |  | < 6 Months | 30025001 | AOGIRTA1001 | Not Compl | 120 | Yes
TA1002 | Fire Detector | Fire Detector inspection for TA1002 | GIR/FPSOH/FIRE/TA1002 | 28/07/2024 | 12 | 28/07/2025 | 2025 | 2025-07-28 | 0 | 7 | 11 |  | < 6 Months | 30025002 | AOGIRTA1002 | Not Compl | 96 | Yes
TA1003 | Flame Arrestor | Flame Arrestor inspection for TA1003 | GIR/FPSOH/FIRE/TA1003 | 17/05/2024 | 12 | 17/05/2025 | 2025 | 2025-05-17 | 0 | 5 | 11 |  | < 6 Months | 30025003 | AOGIRTA1003 | Not Compl | 168 | Yes
TA1004 | Flame Arrestor | Flame Arrestor inspection for TA1004 | GIR/FPSOT/INERT/TA1004 | 14/10/2024 | 12 | 14/10/2025 | 2025 | 2025-10-14 | 0 | 10 | 11 |  | < 6 Months | 30025004 | AOGIRTA1004 | Not Compl | 18 | Yes
TA1005 | Flame Arrestor | Flame Arrestor inspection for TA1005 | GIR/DECK/INERT/TA1005 | 30/06/2024 | 12 | 30/06/2025 | 2025 | 2025-06-30 | 0 | 6 | 11 | SCE | < 6 Months | 30025005 | AOGIRTA1005 | Not Compl | 124 | Yes
TA1006 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1006 | GIR/FPSOH/FIRE/TA1006 | 02/05/2024 | 12 | 02/05/2025 | 2025 | 2025-05-02 | 0 | 5 | 11 |  | > 6 Months | 30025006 | AOGIRTA1006 | Not Compl | 183 | Yes
TA1007 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1007 | GIR/DECK/INERT/TA1007 | 30/05/2024 | 12 | 30/05/2025 | 2025 | 2025-05-30 | 0 | 5 | 11 |  | < 6 Months | 30025007 | AOGIRTA1007 | Not Compl | 155 | Yes
TA1008 | Flame Arrestor | Flame Arrestor inspection for TA1008 | GIR/DECK/STRUC/TA1008 | 11/07/2024 | 12 | 11/07/2025 | 2025 | 2025-07-11 | 0 | 7 | 11 | SCE | < 6 Months | 30025008 | AOGIRTA1008 | Not Compl | 113 | Yes
TA1009 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1009 | GIR/FPSOT/STRUC/TA1009 | 16/09/2024 | 12 | 16/09/2025 | 2025 | 2025-09-16 | 0 | 9 | 11 |  | < 6 Months | 30025009 | AOGIRTA1009 | Not Compl | 46 | Yes
TA1010 | Emergency Lighting | Emergency Lighting inspection for TA1010 | GIR/FPSOT/STRUC/TA1010 | 25/08/2024 | 12 | 25/08/2025 | 2025 | 2025-08-25 | 0 | 8 | 11 | SCE | < 6 Months | 30025010 | AOGIRTA1010 | Not Compl | 68 | Yes
TA1011 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1011 | GIR/FPSOT/HVAC/TA1011 | 16/08/2024 | 12 | 16/08/2025 | 2025 | 2025-08-16 | 0 | 8 | 11 |  | < 6 Months | 30025011 | AOGIRTA1011 | Not Compl | 77 | Yes
TA1012 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1012 | GIR/DECK/HVAC/TA1012 | 18/05/2024 | 12 | 18/05/2025 | 2025 | 2025-05-18 | 0 | 5 | 11 |  | < 6 Months | 30025012 | AOGIRTA1012 | Not Compl | 167 | Yes
TA1013 | Structural Inspection | Structural Inspection inspection for TA1013 | GIR/FPSOT/FIRE/TA1013 | 28/08/2024 | 12 | 28/08/2025 | 2025 | 2025-08-28 | 0 | 8 | 11 | SCE | < 6 Months | 30025013 | AOGIRTA1013 | Not Compl | 65 | Yes
TA1014 | Structural Inspection | Structural Inspection inspection for TA1014 | GIR/FPSOT/UTIL/TA1014 | 26/07/2024 | 12 | 26/07/2025 | 2025 | 2025-07-26 | 0 | 7 | 11 |  | < 6 Months | 30025014 | AOGIRTA1014 | Not Compl | 98 | Yes
TA1015 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1015 | GIR/FPSOT/HVAC/TA1015 | 26/08/2024 | 12 | 26/08/2025 | 2025 | 2025-08-26 | 0 | 8 | 11 | SCE | < 6 Months | 30025015 | AOGIRTA1015 | Not Compl | 67 | Yes
TA1016 | Flame Arrestor | Flame Arrestor inspection for TA1016 | GIR/DECK/UTIL/TA1016 | 13/07/2024 | 12 | 13/07/2025 | 2025 | 2025-07-13 | 0 | 7 | 11 |  | < 6 Months | 30025016 | AOGIRTA1016 | Not Compl | 111 | Yes
TA1017 | Structural Inspection | Structural Inspection inspection for TA1017 | GIR/DECK/ELEC/TA1017 | 30/07/2024 | 12 | 30/07/2025 | 2025 | 2025-07-30 | 0 | 7 | 11 |  | < 6 Months | 30025017 | AOGIRTA1017 | Not Compl | 94 | Yes
TA1018 | Flame Arrestor | Flame Arrestor inspection for TA1018 | GIR/FPSOT/UTIL/TA1018 | 15/04/2024 | 12 | 15/04/2025 | 2025 | 2025-04-15 | 0 | 4 | 11 | SCE | > 6 Months | 30025018 | AOGIRTA1018 | Not Compl | 200 | Yes
TA1019 | Corrosion Monitoring | Corrosion Monitoring inspection for TA1019 | GIR/DECK/ELEC/TA1019 | 16/05/2024 | 12 | 16/05/2025 | 2025 | 2025-05-16 | 0 | 5 | 11 |  | < 6 Months | 30025019 | AOGIRTA1019 | Not Compl | 169 | Yes
TA1020 | Structural Inspection | Structural Inspection inspection for TA1020 | GIR/FPSOH/INERT/TA1020 | 03/09/2024 | 12 | 03/09/2025 | 2025 | 2025-09-03 | 0 | 9 | 11 | SCE | < 6 Months | 30025020 | AOGIRTA1020 | Not Compl | 59 | Yes
TA1021 | Emergency Lighting | Emergency Lighting inspection for TA1021 | GIR/FPSOT/FIRE/TA1021 | 02/10/2024 | 12 | 02/10/2025 | 2025 | 2025-10-02 | 0 | 10 | 11 |  | < 6 Months | 30025021 | AOGIRTA1021 | Not Compl | 30 | Yes
TA1022 | Corrosion Monitoring | Corrosion Monitoring inspection for TA1022 | GIR/DECK/ELEC/TA1022 | 14/10/2024 | 12 | 14/10/2025 | 2025 | 2025-10-14 | 0 | 10 | 11 | SCE | < 6 Months | 30025022 | AOGIRTA1022 | Not Compl | 18 | Yes
TA1023 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1023 | GIR/FPSOH/ELEC/TA1023 | 11/06/2024 | 12 | 11/06/2025 | 2025 | 2025-06-11 | 0 | 6 | 11 |  | < 6 Months | 30025023 | AOGIRTA1023 | Not Compl | 143 | Yes
TA1024 | Flame Arrestor | Flame Arrestor inspection for TA1024 | GIR/FPSOT/INERT/TA1024 | 07/08/2024 | 12 | 07/08/2025 | 2025 | 2025-08-07 | 0 | 8 | 11 |  | < 6 Months | 30025024 | AOGIRTA1024 | Not Compl | 86 | Yes
TA1025 | Fire Detector | Fire Detector inspection for TA1025 | GIR/FPSOH/INERT/TA1025 | 08/09/2024 | 12 | 08/09/2025 | 2025 | 2025-09-08 | 0 | 9 | 11 |  | < 6 Months | 30025025 | AOGIRTA1025 | Not Compl | 54 | Yes
TA1026 | Emergency Lighting | Emergency Lighting inspection for TA1026 | GIR/DECK/FIRE/TA1026 | 13/08/2024 | 12 | 13/08/2025 | 2025 | 2025-08-13 | 0 | 8 | 11 |  | < 6 Months | 30025026 | AOGIRTA1026 | Not Compl | 80 | Yes
TA1027 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1027 | GIR/FPSOH/UTIL/TA1027 | 23/10/2024 | 12 | 23/10/2025 | 2025 | 2025-10-23 | 0 | 10 | 11 |  | < 6 Months | 30025027 | AOGIRTA1027 | Not Compl | 9 | Yes
TA1028 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1028 | GIR/FPSOH/ELEC/TA1028 | 17/06/2024 | 12 | 17/06/2025 | 2025 | 2025-06-17 | 0 | 6 | 11 |  | < 6 Months | 30025028 | AOGIRTA1028 | Not Compl | 137 | Yes
TA1029 | Emergency Lighting | Emergency Lighting inspection for TA1029 | GIR/DECK/INERT/TA1029 | 06/09/2024 | 12 | 06/09/2025 | 2025 | 2025-09-06 | 0 | 9 | 11 | SCE | < 6 Months | 30025029 | AOGIRTA1029 | Not Compl | 56 | Yes
TA1030 | Corrosion Monitoring | Corrosion Monitoring inspection for TA1030 | GIR/FPSOH/STRUC/TA1030 | 30/09/2024 | 12 | 30/09/2025 | 2025 | 2025-09-30 | 0 | 9 | 11 | SCE | < 6 Months | 30025030 | AOGIRTA1030 | Not Compl | 32 | Yes
TA1031 | Structural Inspection | Structural Inspection inspection for TA1031 | GIR/FPSOH/ELEC/TA1031 | 02/08/2024 | 12 | 02/08/2025 | 2025 | 2025-08-02 | 0 | 8 | 11 |  | < 6 Months | 30025031 | AOGIRTA1031 | Not Compl | 91 | Yes
TA1032 | Structural Inspection | Structural Inspection inspection for TA1032 | GIR/FPSOH/HVAC/TA1032 | 04/10/2024 | 12 | 04/10/2025 | 2025 | 2025-10-04 | 0 | 10 | 11 |  | < 6 Months | 30025032 | AOGIRTA1032 | Not Compl | 28 | Yes
TA1033 | Flame Arrestor | Flame Arrestor inspection for TA1033 | GIR/FPSOT/FIRE/TA1033 | 09/07/2024 | 12 | 09/07/2025 | 2025 | 2025-07-09 | 0 | 7 | 11 | SCE | < 6 Months | 30025033 | AOGIRTA1033 | Not Compl | 115 | Yes
TA1034 | Flame Arrestor | Flame Arrestor inspection for TA1034 | GIR/DECK/HVAC/TA1034 | 27/05/2024 | 12 | 27/05/2025 | 2025 | 2025-05-27 | 0 | 5 | 11 | SCE | < 6 Months | 30025034 | AOGIRTA1034 | Not Compl | 158 | Yes
TA1035 | Emergency Lighting | Emergency Lighting inspection for TA1035 | GIR/FPSOH/UTIL/TA1035 | 17/04/2024 | 12 | 17/04/2025 | 2025 | 2025-04-17 | 0 | 4 | 11 |  | > 6 Months | 30025035 | AOGIRTA1035 | Not Compl | 198 | Yes
TA1036 | Flame Arrestor | Flame Arrestor inspection for TA1036 | GIR/FPSOH/FIRE/TA1036 | 04/07/2024 | 12 | 04/07/2025 | 2025 | 2025-07-04 | 0 | 7 | 11 |  | < 6 Months | 30025036 | AOGIRTA1036 | Not Compl | 120 | Yes
TA1037 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1037 | GIR/FPSOH/FIRE/TA1037 | 10/06/2024 | 12 | 10/06/2025 | 2025 | 2025-06-10 | 0 | 6 | 11 |  | < 6 Months | 30025037 | AOGIRTA1037 | Not Compl | 144 | Yes
TA1038 | Flame Arrestor | Flame Arrestor inspection for TA1038 | GIR/FPSOH/STRUC/TA1038 | 18/07/2024 | 12 | 18/07/2025 | 2025 | 2025-07-18 | 0 | 7 | 11 |  | < 6 Months | 30025038 | AOGIRTA1038 | Not Compl | 106 | Yes
TA1039 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1039 | GIR/FPSOT/HVAC/TA1039 | 01/10/2024 | 12 | 01/10/2025 | 2025 | 2025-10-01 | 0 | 10 | 11 | SCE | < 6 Months | 30025039 | AOGIRTA1039 | Not Compl | 31 | Yes
TA1040 | Fire Detector | Fire Detector inspection for TA1040 | GIR/DECK/FIRE/TA1040 | 05/08/2024 | 12 | 05/08/2025 | 2025 | 2025-08-05 | 0 | 8 | 11 |  | < 6 Months | 30025040 | AOGIRTA1040 | Not Compl | 88 | Yes
TA1041 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1041 | GIR/FPSOT/UTIL/TA1041 | 08/10/2024 | 12 | 08/10/2025 | 2025 | 2025-10-08 | 0 | 10 | 11 |  | < 6 Months | 30025041 | AOGIRTA1041 | Not Compl | 24 | Yes
TA1042 | Fire Detector | Fire Detector inspection for TA1042 | GIR/DECK/STRUC/TA1042 | 21/10/2024 | 12 | 21/10/2025 | 2025 | 2025-10-21 | 0 | 10 | 11 | SCE | < 6 Months | 30025042 | AOGIRTA1042 | Not Compl | 11 | Yes
TA1043 | Emergency Lighting | Emergency Lighting inspection for TA1043 | GIR/FPSOT/STRUC/TA1043 | 28/04/2024 | 12 | 28/04/2025 | 2025 | 2025-04-28 | 0 | 4 | 11 |  | > 6 Months | 30025043 | AOGIRTA1043 | Not Compl | 187 | Yes
TA1044 | Flame Arrestor | Flame Arrestor inspection for TA1044 | GIR/FPSOH/UTIL/TA1044 | 11/08/2024 | 12 | 11/08/2025 | 2025 | 2025-08-11 | 0 | 8 | 11 |  | < 6 Months | 30025044 | AOGIRTA1044 | Not Compl | 82 | Yes
TA1045 | Flame Arrestor | Flame Arrestor inspection for TA1045 | GIR/DECK/STRUC/TA1045 | 26/05/2024 | 12 | 26/05/2025 | 2025 | 2025-05-26 | 0 | 5 | 11 |  | < 6 Months | 30025045 | AOGIRTA1045 | Not Compl | 159 | Yes
TA1046 | Fire Detector | Fire Detector inspection for TA1046 | GIR/FPSOH/ELEC/TA1046 | 17/10/2024 | 12 | 17/10/2025 | 2025 | 2025-10-17 | 0 | 10 | 11 |  | < 6 Months | 30025046 | AOGIRTA1046 | Not Compl | 15 | Yes
TA1047 | Pressure Relief Valve | Pressure Relief Valve inspection for TA1047 | GIR/DECK/ELEC/TA1047 | 28/10/2024 | 12 | 28/10/2025 | 2025 | 2025-10-28 | 0 | 10 | 11 |  | < 6 Months | 30025047 | AOGIRTA1047 | Not Compl | 4 | Yes
TA1048 | Structural Inspection | Structural Inspection inspection for TA1048 | GIR/DECK/UTIL/TA1048 | 27/06/2024 | 12 | 27/06/2025 | 2025 | 2025-06-27 | 0 | 6 | 11 |  | < 6 Months | 30025048 | AOGIRTA1048 | Not Compl | 127 | Yes
TA1049 | Flame Arrestor | Flame Arrestor inspection for TA1049 | GIR/FPSOH/HVAC/TA1049 | 15/04/2024 | 12 | 15/04/2025 | 2025 | 2025-04-15 | 0 | 4 | 11 | SCE | > 6 Months | 30025049 | AOGIRTA1049 | Not Compl | 200 | Yes